## Projecttijdlijn
Project timeline
Start Date | 2022-02-21
Sprint | 1.2 | [6 empty] | X | [6 empty] | 1.3 | [6 empty] | 2.1 | [6 empty] | 2.2 | [6 empty] | 2.3 | [6 empty] | 3.1 | [6 empty] | 3.2 | [6 empty] | 3.3
Week | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9
| feb | [6 empty] | feb | mrt | [5 empty] | mrt | [6 empty] | mrt | [6 empty] | mrt | [6 empty] | mrt |  |  |  | apr |  |  | apr | [6 empty] | apr | [6 empty] | apr
| ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo
 | time axis 2022-02-21 to 2022-04-24
Current goal | 2022-02-21: Project Setup; 2022-02-23: Design documentation; 2022-02-25: 140 hour project; 2022-02-26: Weekend; 2022-02-28: Spring break; 2022-03-05: Weekend; 2022-03-07: Design documentation; 2022-03-10: Demo; 2022-03-11: 140 hour project; 2022-03-12: Weekend; 2022-03-14: Creating ML Algorithm; 2022-03-18: 140 hour project; 2022-03-19: Weekend; 2022-03-21: Creating ML Algorithm; 2022-03-25: 140 hour project; 2022-03-26: Weekend; 2022-03-28: Create ML Algorithm and; 2022-03-31: Demo; 2022-04-01: 140 hour project; 2022-04-02: Weekend; 2022-04-04: Creating ML Algorithm; 2022-04-08: 140 hour project; 2022-04-09: Weekend; 2022-04-11: Creating ML Algorithm; 2022-04-15: Good Friday; 2022-04-16: Weekend; 2022-04-18: East-er; 2022-04-19: Creating ML Algorithm; 2022-04-21: Demo; 2022-04-22: 140 hour project; 2022-04-23: Weekend
Products/details | 2022-02-21: Project timeline and GitHub board; 2022-02-23: Requirement document; 2022-02-24: Requirement document; 2022-03-07: Class diagram and start dashboard prototype; 2022-03-10: Add Retrospect; 2022-03-14: Research image recognition technology; 2022-03-21: Investigate data set; 2022-03-23: Research possibility of extending dataset; 2022-03-28: Create code to train the algorithm; 2022-03-31: Add Retrospect; 2022-04-04: Create code to train the algorithm; 2022-04-11: Test and Optimize Algorithm; 2022-04-19: Test and Optimize Algorithm; 2022-04-21: Add Retrospect
Sprint | 2022-02-21: 4.1; 2022-02-28: X; 2022-03-07: 4.2; 2022-03-14: 4.3; 2022-03-21: 5.1; 2022-03-28: 5.1; 2022-04-04: 5.2; 2022-04-11: 5.3; 2022-04-18: Semester end
Week | 2022-02-21: Week 10; 2022-02-28: Week 11; 2022-03-07: Week 12; 2022-03-14: Week 13; 2022-03-21: Week 14; 2022-03-28: Week 15; 2022-04-04: Week 16; 2022-04-11: Week 17; 2022-04-18: Week 18
| apr | [5 empty] | mei | mei | [6 empty] | mei | [6 empty] | mei | [6 empty] | mei | [6 empty] | mei |  | jun |  |  |  |  | jun | [6 empty] | jun | [6 empty] | jun
| ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo
 | time axis 2022-04-25 to 2022-06-26
Current goal | 2022-04-25: Creating Dashboard; 2022-04-27: Kings day; 2022-04-28: Dashboard; 2022-04-29: 140 hour project; 2022-04-30: Weekend; 2022-05-02: May break; 2022-05-07: Weekend; 2022-05-09: Creating Dashboard; 2022-05-13: 140 hour project; 2022-05-14: Weekend; 2022-05-16: Dashboard; 2022-05-17: Study day; 2022-05-18: Dashboard; 2022-05-19: Demo; 2022-05-20: 140 hour project; 2022-05-21: Weekend; 2022-05-23: Creating Dashboard; 2022-05-26: Ascension Day; 2022-05-28: Weekend; 2022-05-30: Creating Dashboard; 2022-06-03: 140 hour project; 2022-06-04: Weekend; 2022-06-06: White Monday; 2022-06-07: Creating Dashboard; 2022-06-10: 140 hour project; 2022-06-11: Weekend; 2022-06-13: End documentation and Extra time for delays; 2022-06-16: Demo; 2022-06-17: 140 hour project; 2022-06-18: Weekend; 2022-06-20: End talk/presentation; 2022-06-25: Weekend
Products/details | 2022-04-25: Create prototype and start fronted; 2022-04-28: Create Front end; 2022-05-09: Create Front end; 2022-05-10: Implement image import and data cleaning; 2022-05-16: Image Import; 2022-05-18: Image Import; 2022-05-19: Add Retrospect; 2022-05-23: Setup ML algorithm in the dashboard; 2022-05-30: Connect Algorithm with Import image system; 2022-06-07: Testing dashboard